JayQuery

Privacy-Preserving Student Success Prediction with Federated Learning

Detailed 10-Week Research & Software Implementation Plan

SCARP 2026 — Elizabethtown College

| Field | Detail |
| --- | --- |
| Project Title | JayQuery: Privacy-Preserving Student Success Prediction with Federated Learning |
| Mentor | Dr. Peilong Li (lip@etown.edu), Associate Professor of Computer Science |
| Student A | Alex Pellet (pellet@etown.edu) — System Architect & ML Engineer [Senior] |
| Student B | Wyatt Wilfong (wilfong@etown.edu) — Privacy & Security Lead [Freshman] |
| Duration | 10 Weeks, Full-Time (40 hrs/week) |
| Core Stack | Python 3.11 ¦ PyTorch 2.2 ¦ Flower (flwr) 1.8 ¦ Opacus 1.4 ¦ scikit-learn ¦ XGBoost |
| Dataset | Open University Learning Analytics Dataset (OULAD) |

🔵  Blue / Teal  =  Student A (Alex) — System Architecture, ML Models, Data Engineering

🟣  Purple  =  Student B (Wyatt) — Privacy, Cryptography, Differential Privacy, Red Team

1. Project Overview & Revised Role Structure

## 1.1 Research Objective

JayQuery builds a Vertical Federated Learning (VFL) system that trains a Student Success prediction neural network across two simulated institutional data silos — Financial Aid (Silo A) and Academic Affairs (Silo B) — without ever centralizing raw student records. The two students bring complementary strengths: Alex architects the overall system and builds all machine learning models, while Wyatt focuses exclusively on the cryptographic and privacy-engineering components that make the system FERPA-compliant.

## 1.2 Division of Responsibilities

| Student | Responsibilities |
| --- | --- |
| Alex Pellet (Student A) System Architect & ML Engineer | Flower framework server + client infrastructure ¦ OULAD dataset download, EDA, and silo construction ¦ Feature engineering for both Silo A and Silo B ¦ All Bottom Models (A & B) and Top Model in PyTorch ¦ Centralized and isolated-silo baselines ¦ Experiment orchestration ¦ Hyperparameter tuning & ablation studies ¦ VFL training loop ¦ Temporal sufficiency analysis ¦ SHAP feature importance ¦ Architecture documentation ¦ Paper Methods + Results sections |
| Wyatt Wilfong (Student B) Privacy & Security Lead | Private Set Intersection (PSI) protocol implementation (step-by-step guided) ¦ Differential Privacy wrapper using Opacus (detailed tutorials provided per step) ¦ Privacy Accountant (RDP budget tracking) ¦ Differential Privacy experiments across the epsilon grid ¦ Model Inversion Attack (iDLG / gradient-matching, with code scaffold) ¦ Label inference attack ¦ Threat model documentation ¦ Privacy analysis write-up ¦ Attack demo notebook |

## 1.3 Special Mentoring Plan

Because Wyatt is a first-year student, every privacy task in this plan is decomposed into numbered, executable sub-steps with detailed commands, starter code skeletons, expected outputs to validate against, and explicit escalation triggers. The goal is that Wyatt never has to stare at a blank file — every module starts with a provided scaffold. Alex is expected to operate more independently, making design decisions with mentor sign-off rather than step-by-step scripts.

📌  All purple-shaded boxes throughout this document are Wyatt's step-by-step scaffolded guides. If Wyatt is stuck for more than 60 minutes on any step, he must message Dr. Li on Slack immediately — do not wait for Wednesday.

2. Required Reading List

★ = must read in full.  No star = read abstract + introduction + conclusion, skim the rest. Both students complete the shared readings in Week 1 together during the Monday deep-dive session.

## 2.1 Shared Foundational Reading — Both Students, Week 1

| Paper / Resource | Authors & Year | Topic Area | Required By |
| --- | --- | --- | --- |
| ★ Communication-Efficient Learning of Deep Networks from Decentralized Data (FedAvg) | McMahan et al., 2017 (AISTATS) | Horizontal FL — project vocabulary baseline | Week 1 |
| ★ Federated Machine Learning: Concept and Applications | Yang et al., 2019 (ACM TIST) | VFL vs HFL taxonomy — the core framing paper | Week 1 |
| ★ Split Learning for Health (SplitNN) | Vepakomma et al., 2018 (ICLR Wksp) | The SplitNN architecture this project implements | Week 1 |
| ★ Open University Learning Analytics Dataset (OULAD) | Kuzilek et al., 2017 (Scientific Data) | Dataset paper — read before any code is written | Week 1 |
| Advances and Open Problems in Federated Learning | Kairouz et al., 2021 (FnTML) | Comprehensive FL survey; focus VFL + non-IID sections | Week 2 |

## 2.2 Student A (Alex) — ML Engineering, Architecture & Data Track

Alex is expected to pursue these papers with an architectural mindset — read for design decisions, not just understanding. After each paper, write a one-paragraph design note in docs/alex_paper_notes.md on what implementation choice it informs.

| Paper / Resource | Authors & Year | Topic Area | Required By |
| --- | --- | --- | --- |
| ★ SplitFed: When Federated Learning Meets Split Learning | Thapa et al., 2022 (AAAI) | Hybrid design — informs Bottom/Top model split decisions | Week 2 |
| Efficient Vertical Federated Learning with Secure Aggregation | Xu et al., 2021 (arXiv) | VFL gradient alignment and communication efficiency | Week 3 |
| ★ Predicting Student Performance: A Shape of Educational Data | Kotsiantis et al., 2010 (MIPRO) | Feature engineering for student outcome prediction | Week 3 |
| XGBoost: A Scalable Tree Boosting System | Chen & Guestrin, 2016 (KDD) | Centralized baseline — read Section 2 (algorithm) only | Week 4 |
| An Introduction to ROC Analysis | Fawcett, 2006 (Pattern Recog. Letters) | AUC-ROC — evaluation methodology for imbalanced EDM data | Week 4 |
| ★ Tackling the Objective Inconsistency Problem in HFL | Wang et al., 2020 (NeurIPS) | Non-IID challenges — informs training stability decisions | Week 5 |
| SMOTE: Synthetic Minority Over-Sampling Technique | Chawla et al., 2002 (JAIR) | Class imbalance in OULAD dropout labels | Week 3 |
| Educational Data Mining: A Review of the State of the Art | Romero & Ventura, 2010 (IEEE TKDE) | EDM context + prior student success prediction work | Week 2 |
| The Privacy-Utility Tradeoff for Machine Learning with DP | Jayaraman & Evans, 2019 (USENIX) | Informs tradeoff experiment design (shared with Wyatt) | Week 7 |

## 2.3 Student B (Wyatt) — Privacy, Cryptography & Security Track

Wyatt's reading is sequenced to build understanding incrementally. Each paper is paired with a concrete "reading task" to ensure comprehension is connected to code. Dr. Li will provide 1-page reading guides for the two most technical papers (Dwork & Roth, Abadi) to highlight the essential sections.

| Paper / Resource | Authors & Year | Topic Area | Required By |
| --- | --- | --- | --- |
| ★ The Algorithmic Foundations of Differential Privacy (Ch. 1–4 only) | Dwork & Roth, 2014 (FnTCS) | DP formal definitions, sensitivity, Gaussian mechanism — Dr. Li provides reading guide | Week 2 |
| ★ Deep Learning with Differential Privacy (DP-SGD) | Abadi et al., 2016 (ACM CCS) | DP applied to neural net training — the core Opacus paper. Dr. Li provides reading guide | Week 3 |
| Rényi Differential Privacy of the Gaussian Mechanism (Sections 1–3 only) | Mironov, 2017 (IEEE CSF) | RDP accountant — read to understand what epsilon means at each training step | Week 4 |
| ★ Scalable Private Set Intersection Based on OT Extension | Pinkas et al., 2018 (ACM CCS) | PSI protocol — focus on Sections 1–3 (protocol overview, not full proof) | Week 2 |
| Private Set Intersection: Are Garbled Circuits Better? (Sections 1–2 only) | Huang et al., 2012 (NDSS) | Why ECDH-based PSI is chosen over GC for this scale | Week 3 |
| ★ Model Inversion Attacks that Exploit Confidence Information | Fredrikson et al., 2015 (ACM CCS) | Original model inversion formulation — read Sections 1–4 | Week 7 |
| ★ Deep Leakage from Gradients (iDLG) | Zhao et al., 2020 (NeurIPS) | Primary Red Team attack method — read full paper, focus on Algorithm 1 | Week 7 |
| CAFE: Catastrophic Data Leakage in Vertical Federated Learning (Sections 1–4) | Jin et al., 2021 (NeurIPS) | VFL-specific attack — most directly relevant to this project | Week 8 |
| Label Leakage and Protection in Two-party Split Learning | Li et al., 2022 (ICLR) | Label inference attack — secondary Red Team method | Week 8 |

📌  Wyatt: after reading each paper, write 3–5 bullet points in docs/wyatt_paper_notes.md: (1) what the paper does, (2) one thing that surprised you, (3) which part of our project it relates to. Share with Dr. Li before the Monday meeting.

3. Software Frameworks & Environment Setup

## 3.1 Development Environment (Both Students)

- OS: Ubuntu 22.04 LTS or WSL2 on Windows. Both students must be on the same OS configuration.

- Python: 3.11.x via pyenv. Both students run: pyenv install 3.11.8 && pyenv local 3.11.8

- Conda environment: conda create -n jayquery python=3.11 && conda activate jayquery

- IDE: VS Code with Python + Pylance. Both install the same extensions (saved to .vscode/extensions.json in repo).

- Git: GitHub repo https://github.com/Peilong/JayQuery. Daily commits required. Use branches: feat/[module-name]. Open PR each Friday.

- Experiment Tracking: Weights & Biases (wandb.ai). Free academic tier. Both create accounts and join the shared jayquery team project.

🔒  WYATT — Step-by-Step: Environment Setup (Do This in Week 1)

- Install WSL2 (Windows) or verify Ubuntu 22.04 is running. Open a terminal.

wsl --install  (Windows) OR  lsb_release -a  (Linux — verify Ubuntu 22.04)

- Install pyenv to manage Python versions:

curl https://pyenv.run | bash   # then follow the 3 export lines it prints into ~/.bashrc

- Install Python 3.11 and create the project environment:

pyenv install 3.11.8 && pyenv global 3.11.8 && pip install --upgrade pip

- Clone the repo and install all packages:

git clone https://github.com/Peilong/JayQuery && cd jayquery && pip install -r requirements.txt

- Verify key packages loaded correctly (run python and type these):

import torch; print(torch.__version__)   # should print 2.2.x

import flwr; print(flwr.__version__)     # should print 1.8.x

import opacus; print(opacus.__version__) # should print 1.4.x

💡 If stuck: If any import fails with ModuleNotFoundError, run: pip install [package-name] --upgrade. If it still fails, post the exact error in Slack immediately.

## 3.2 Python Packages

| Component | Technology | Specification | Owner |
| --- | --- | --- | --- |
| Core ML | PyTorch 2.2 + torchvision | pip install torch torchvision --index-url https://download.pytorch.org/whl/cu121. Alex builds all models with this. | Alex |
| Federated Framework | Flower (flwr) 1.8 | pip install flwr — Alex uses this for server/client orchestration. Wyatt uses it only to send/receive embeddings via the cut layer. | Alex |
| Differential Privacy | Opacus 1.4 | pip install opacus — Wyatt's primary tool. Wraps PyTorch optimizer with DP-SGD (per-sample gradient clipping + Gaussian noise). | Wyatt |
| Privacy Accounting | autodp 0.2 | pip install autodp — Wyatt uses this for RDP epsilon budget tracking across training rounds. | Wyatt |
| Cryptography (PSI) | cryptography 42.x + pycryptodome 3.20 | pip install cryptography pycryptodome — Wyatt uses for ECDH key exchange in PSI module. | Wyatt |
| Data Processing | pandas 2.2 + numpy 1.26 | pip install pandas numpy — Alex uses for OULAD loading and feature engineering. | Alex |
| ML Baselines | scikit-learn 1.4 + xgboost 2.0 | pip install scikit-learn xgboost — Alex builds centralized baseline models. | Alex |
| Imbalance Handling | imbalanced-learn 0.12 | pip install imbalanced-learn — Alex applies SMOTE during silo construction. | Alex |
| Experiment Tracking | wandb 0.17 | pip install wandb — Both students log training runs. All experiments must be tagged with student name and week number. | Both |
| Visualization | matplotlib 3.8 + seaborn 0.13 + plotly 5.20 | pip install matplotlib seaborn plotly — Alex produces all training curves and tradeoff plots. | Alex |
| Networking (IPC) | grpc 1.63 + protobuf 4.25 | pip install grpcio grpcio-tools protobuf — Alex designs the inter-silo channel; Wyatt uses the provided client stub only. | Alex |
| Testing | pytest 8.x + pytest-cov | pip install pytest pytest-cov — Both write unit tests. Wyatt's tests provided as scaffolds; Alex writes from scratch. | Both |
| Jupyter | jupyter 1.0 + ipywidgets | pip install jupyter ipywidgets — Alex: EDA notebook. Wyatt: attack demo notebook. | Both |

## 3.3 Repository Structure

Alex designs and initializes this structure in Week 1. Wyatt follows the layout exactly — do not create files outside the designated folders.

- jayquery/  — project root

  - data/  — raw OULAD CSVs (gitignored), silo_a.pkl, silo_b.pkl  [Alex creates these]

  - fl_server/  — server.py, top_model.py, vfl_strategy.py  [Alex]

  - silo_a/  — client_a.py, bottom_model_a.py, data_loader_a.py  [Alex]

  - silo_b/  — client_b.py, bottom_model_b.py, data_loader_b.py  [Alex]

  - psi/  — psi_client.py, psi_server.py, ecdh_utils.py, test_psi.py  [Wyatt — scaffold provided by Alex Week 2]

  - privacy/  — dp_wrapper.py, privacy_accountant.py, noise_injection.py  [Wyatt — scaffolds provided]

  - attack/  — inversion.py, label_inference.py, gradient_monitor.py  [Wyatt — scaffolds provided Week 7]

  - baselines/  — centralized_mlp.py, centralized_xgb.py, eval_utils.py  [Alex]

  - experiments/  — YAML configs, wandb sweep files, checkpoints/  [Alex]

  - notebooks/  — eda.ipynb [Alex], attack_demo.ipynb [Wyatt], tradeoff_analysis.ipynb [Alex]

  - docs/  — alex_paper_notes.md, wyatt_paper_notes.md, weekly reports, final paper draft, protocol_spec.md, threat_model.md, privacy_analysis.md

  - tests/  — test_psi.py [Wyatt], test_dp.py [Wyatt], test_models.py [Alex], test_loaders.py [Alex]

4. Deep Learning Model Specifications  [Alex owns all models]

All PyTorch model files are owned and implemented by Alex. Wyatt does NOT write model code — he only wraps Alex's optimizer with Opacus in privacy/dp_wrapper.py. The split is clean: Alex builds the network; Wyatt adds the privacy layer on top of it.

## 4.1 Bottom Model A — Silo A (Financial Aid / Demographics)

Input: 12 features from OULAD studentInfo.csv — imd_band (deprivation index, ordinal-encoded), highest_education (ordinal), age_band (ordinal), gender (binary), disability (binary), region (one-hot, 8 dims), studied_credits (continuous, normalized). Owned by Alex.

| Component | Technology | Specification | Owner |
| --- | --- | --- | --- |
| Architecture | MLP + Batch Norm | Input(12) → Linear(64) → BN → ReLU → Dropout(0.3) → Linear(64) → BN → ReLU → Linear(32) | Alex |
| Output | 32-dim embedding | Raw logit vector — no activation on output. This is the 'cut layer' payload transmitted to Top Model via Flower. | Alex |
| Optimizer | Adam lr=1e-3 | Standard Adam. Wyatt wraps this with Opacus PrivacyEngine for DP-enabled runs. | Alex / Wyatt |
| Regularization | Dropout(0.3) + BN | BN before ReLU. Dropout combats overfitting on sparse tabular features. | Alex |
| DP Wrapping | Opacus PrivacyEngine | Wyatt wraps Alex's optimizer using the scaffold in privacy/dp_wrapper.py. max_grad_norm=1.0 default. | Wyatt |

## 4.2 Bottom Model B — Silo B (Academic Affairs / VLE + Assessments)

Input: 22 features from OULAD studentAssessment.csv + studentVle.csv — per-activity click counts (15 VLE activity types, sum-aggregated per student), weighted average assessment score, num_assessments_submitted, days_active, total_activity_types_used. Owned by Alex.

| Component | Technology | Specification | Owner |
| --- | --- | --- | --- |
| Architecture | MLP with residual skip | Input(22) → Linear(128) → BN → ReLU → Linear(64) → BN → ReLU → Linear(64) [+skip 128→64 via Linear projection] → Linear(32) | Alex |
| Output | 32-dim embedding | Same dimensionality as Model A. Concatenated at Top Model: [emb_A ¦ emb_B] = 64-dim input. | Alex |
| Architecture rationale | Skip connection | VLE interaction data is sparser and noisier; skip connection preserves low-level signal. Alex documents design choice in alex_paper_notes.md. | Alex |
| Optional extension | 1D-CNN variant | If Weeks 5–6 allow, Alex may replace the MLP hidden layers with a 1D-Conv over week-binned VLE time series. Flag as experiment variant. | Alex |
| DP Wrapping | Opacus PrivacyEngine | Wyatt wraps this optimizer identically to Model A. Independent PrivacyEngine instance. | Wyatt |

## 4.3 Top Model — Central Aggregation Server

Receives concatenated [emb_A ‖ emb_B] = 64-dim tensor. Hosted in fl_server/top_model.py. Owned by Alex. This model never leaves the server — only loss and gradient tensors are sent back to the silos.

| Component | Technology | Specification | Owner |
| --- | --- | --- | --- |
| Architecture | Shallow classifier MLP | Input(64) → Linear(64) → ReLU → Dropout(0.2) → Linear(32) → ReLU → Linear(1) | Alex |
| Loss | BCEWithLogitsLoss | pos_weight = (N_neg / N_pos) tensor for class imbalance. No sigmoid in model — loss applies it internally. | Alex |
| Output | Scalar P(dropout risk) | Threshold at 0.5 for class prediction. Raw logit used for AUC-ROC. | Alex |
| Gradient return | dL/d_emb_A, dL/d_emb_B | Server backprops through Top Model, slices the 64-dim gradient into two 32-dim tensors, returns them to respective silo clients via Flower. | Alex |

## 4.4 Centralized Baselines  [Alex only]

- Logistic Regression (scikit-learn): L2, C=1.0. Linear baseline — sets the floor.

- Full MLP (PyTorch): Same architecture as Top Model but raw 34-dim input. Identical hyperparameters for fair comparison.

- XGBoost Classifier: n_estimators=200, max_depth=5, learning_rate=0.05, scale_pos_weight tuned for imbalance.

- Isolated Silo Baselines: MLP trained on only Silo A features; MLP on only Silo B. Quantifies the VFL collaboration benefit.

5. Week-by-Week Research & Implementation Plan

Color legend:     Teal = Alex (Student A)      Purple = Wyatt (Student B, freshman — detailed sub-steps in boxes below each table)

## Phase 1: Weeks 1–3 — Infrastructure, Data Preparation & Privacy Foundations

| Week | Role | Detailed Activities & Goals | Weekly Deliverable |
| --- | --- | --- | --- |
| 1 | Alex System Architect | - Complete SCARP orientation + RCR training (mandatory — do first) - Read all 5 shared foundational papers (see Section 2.1); write design notes in alex_paper_notes.md - Initialize GitHub repo with the full directory structure from Section 3.3; push to GitHub - Install all packages; verify Flower quickstart example runs end-to-end (flwr.simulation quickstart) - Download OULAD dataset (7 CSVs) from analyse.kmi.open.ac.uk/open_dataset; place in data/raw/ - Begin EDA in notebooks/eda.ipynb: load all 7 CSVs, check shapes, dtypes, null counts, distributions - Define binary label: Withdrawn + Fail → 1 (at-risk), Pass + Distinction → 0; document rationale - Set up wandb team project 'jayquery'; invite Wyatt and Dr. Li - Draw system architecture diagram (draw.io): PSI → Bottom Models → Cut Layer → Top Model; share with mentor | GitHub repo initialized + architecture diagram + SETUP.md + EDA notebook (eda.ipynb) + wandb project created |
| 1 | Wyatt Privacy Lead (Freshman) | - Complete SCARP orientation + RCR training (mandatory — do first) - Read all 5 shared foundational papers with a focus on understanding the 'why' (not code yet) - Follow the step-by-step environment setup guide in Section 3.1 of this document — verify all imports - Clone the GitHub repo Alex initialized; confirm you can open and run the quickstart Flower example - Read: Dwork & Roth 2014 Chapter 1 (Definition 2.4: pure DP) and Pinkas 2018 Abstract + Section 1 - Write your first wyatt_paper_notes.md entry with 3–5 bullets on each paper (see Section 2.3 note) - Watch 30-min YouTube explainer on 'Differential Privacy explained simply' (link in docs/resources.md) | Environment verified (screenshot of all imports passing) + wyatt_paper_notes.md first entry + repo cloned |
| 2 | Alex System Architect | - Read: Kairouz 2021 (VFL sections), Thapa 2022, Romero 2010 - Select one OULAD module presentation for scope (recommend BBB_2013J — largest cohort, ~7k students) - Feature engineering for Silo A: encode imd_band, highest_education, age_band (ordinal), region (one-hot), normalize studied_credits; save to data/silo_a_features.pkl - Begin feature engineering for Silo B: pivot studentVle.csv by id_student × activity_type to get click-count matrix; join with studentAssessment.csv aggregates - Implement data/data_utils.py: apply SMOTE to training set; 80/10/10 split (seed=42); write DATA_DICTIONARY.md documenting every column, encoding decision, and null-handling strategy - Write unit tests in tests/test_loaders.py: verify silo shapes, label distribution, no NaN leakage - Design PSI message protocol on paper; hand Wyatt a sketch of the PSI API contract (what inputs/outputs psi_client.py and psi_server.py must expose) - Provide Wyatt with psi/ecdh_utils_scaffold.py — a skeleton file with function stubs and docstrings | Silo A feature file + Silo B feature file + DATA_DICTIONARY.md + PSI scaffold handed to Wyatt |
| 2 | Wyatt Privacy Lead | - Read: Dwork & Roth 2014 Ch. 1–4 (with Dr. Li reading guide); Pinkas 2018 Sections 1–3 - Complete wyatt_paper_notes.md for both papers before Monday meeting - Receive psi/ecdh_utils_scaffold.py from Alex — read all docstrings carefully - Study Python's cryptography library: run the ECDH quickstart example in docs/resources.md - Implement ecdh_utils.py Step A: generate_keypair() → returns (private_key, public_key) using SECP256R1 curve - Implement ecdh_utils.py Step B: blind_id(id_string, private_key) → hashes id to curve point and applies scalar multiplication - Run provided unit test: pytest tests/test_psi.py::test_ecdh_basic — it should PASS - Post Wednesday mid-week report to Dr. Li | ecdh_utils.py with generate_keypair() + blind_id() implemented + test_ecdh_basic passing |
| 3 | Alex System Architect | - Read: Kotsiantis 2010, Chawla 2002 (SMOTE), Xu 2021 - Finalize silo construction: once Wyatt's PSI is ready (end of this week), reorder silo_a.pkl and silo_b.pkl rows to match PSI intersection ID order - Implement silo_a/data_loader_a.py + silo_b/data_loader_b.py: PyTorch Dataset + DataLoader; include get_item(), __len__(), and a validate_alignment(loader_a, loader_b) utility - Implement and run all 4 centralized baselines (LogReg, Full MLP, XGBoost, isolated silos); log results to wandb; produce docs/baseline_results.md table - Build Flower server scaffold: fl_server/server.py with VFLStrategy stub (fit_round, evaluate_round); fl_server/top_model.py stub (forward, compute_gradients) - Build Flower client scaffolds: silo_a/client_a.py + silo_b/client_b.py — with TODO comments marking where Wyatt's DP wrapper will be inserted - Measure PSI protocol timing together with Wyatt: 1k, 5k, 10k ID sets; record in experiments/psi_timing.csv | DataLoaders + all baselines running + baseline_results.md + Flower server/client scaffolds + psi_timing.csv |
| 3 | Wyatt Privacy Lead | - Read: Huang 2012 Sections 1–2; Abadi 2016 Abstract + Sections 1–3 - Implement psi/psi_server.py Step A: receive blinded IDs from client, blind them again with server key, return doubly-blinded set - Implement psi/psi_client.py Step A: send blinded IDs to server, receive doubly-blinded server IDs and doubly-blinded client IDs back, compute intersection via set equality - Run full PSI correctness test: pytest tests/test_psi.py::test_psi_correctness — two Python processes, 1000 IDs, 800 true intersection — intersection result must be exactly 800 - Produce ordered_id_list.json: list of student IDs in PSI intersection order — Alex will use this to align DataLoaders - Collaborate with Alex: run joint timing benchmark (psi/benchmark.py provided by Alex); record results in psi_timing.csv - Document PSI protocol: write 1-page docs/psi_protocol.md explaining each message in plain English (who sends what, when) | Full PSI protocol functional (both processes) + correctness test passing + ordered_id_list.json + psi_protocol.md |

🔒  WYATT — Step-by-Step: Implementing the PSI Protocol (Weeks 2–3)

This is the most complex thing you will build in this project. Follow each step in order. Do not skip ahead.

- Open psi/ecdh_utils_scaffold.py (provided by Alex). Read every docstring. Do not change function signatures.

- Implement generate_keypair(): Use the cryptography library. Exact code pattern:

from cryptography.hazmat.primitives.asymmetric.ec import generate_private_key, SECP256R1

from cryptography.hazmat.backends import default_backend

private_key = generate_private_key(SECP256R1(), default_backend())

public_key = private_key.public_key()

return private_key, public_key

- Implement blind_id(id_str, private_key): hash the string to bytes, then derive a shared point using ECDH exchange with a deterministic peer key. Alex will show you this pattern in Week 2 Monday meeting.

- Run pytest tests/test_psi.py::test_ecdh_basic. You should see 1 passed. If not, post the error in Slack.

- Implement psi_server.py: It is a simple loop: (a) receive blinded IDs list from client over a socket, (b) apply server's own blinding to each, (c) send back the doubly-blinded set.

- Implement psi_client.py: (a) blind your own IDs, (b) send to server, (c) receive doubly-blinded server set AND your own doubly-blinded set back, (d) the intersection = IDs in both sets.

- Run the correctness test: pytest tests/test_psi.py::test_psi_correctness. Expected output: '800 IDs in intersection. PASSED.'

- Write psi_protocol.md: draw a simple ASCII diagram showing the 3 messages exchanged. Alex will review this on Friday.

💡 If stuck: The most common mistake is forgetting to sort both sets before comparing. Python sets are unordered — always convert to sorted lists before intersection.

## Phase 2: Weeks 4–7 — Model Development, VFL Training & DP Integration

| Week | Role | Detailed Activities & Goals | Weekly Deliverable |
| --- | --- | --- | --- |
| 4 | Alex ML Engineer | - Read: Fawcett 2006 (ROC), Chen & Guestrin 2016 (XGBoost) - Implement silo_a/bottom_model_a.py: full PyTorch nn.Module per Section 4.1 spec; include forward(), get_embedding(), and a method signature comment noting where Wyatt will plug in DP - Implement silo_b/bottom_model_b.py: Bottom Model B per Section 4.2; include optional 1D-CNN variant as a flag in __init__ - Implement fl_server/top_model.py: TopModel class with forward() and compute_loss_and_gradients(emb_a, emb_b, labels) → returns (loss, grad_a, grad_b) - Write unit tests tests/test_models.py: verify output shapes match spec, gradients flow correctly (.grad not None after backward), frozen embedding doesn't update - Implement baselines/eval_utils.py: compute_metrics(y_true, y_pred_prob) → dict{AUC, Accuracy, F1, Precision, Recall, Brier} - Smoke test: manually concatenate embeddings from both models, run through TopModel, backprop, print gradient shapes — ensure everything is connected | Bottom Models A&B + Top Model + unit tests passing + eval_utils.py + smoke test verified |
| 4 | Wyatt Privacy Lead | - Read: Mironov 2017 Sections 1–3 (RDP accountant); complete Abadi 2016 reading - Receive Alex's bottom_model_a.py — read the file carefully, identify the optimizer object (e.g., optimizer = Adam(model.parameters(), lr=1e-3)) - Study the Opacus quickstart tutorial at opacus.ai/tutorials/ — run the MNIST DP example in a Jupyter notebook to see DP-SGD in action before touching project code - Implement privacy/dp_wrapper.py: a function make_private(model, optimizer, data_loader, target_epsilon, target_delta, max_grad_norm) that calls PrivacyEngine.make_private_with_epsilon() and returns (dp_model, dp_optimizer, dp_data_loader) - Write tests/test_dp.py::test_dp_wrapper_basic: wrap a 2-layer MLP, run 1 batch, assert optimizer.privacy_engine is not None - Post Wednesday mid-week report | dp_wrapper.py with make_private() implemented + test_dp_wrapper_basic passing + Opacus MNIST demo run |
| 5 | Alex ML Engineer | - Read: Wang 2020 (non-IID), Thapa 2022 (full) - Implement silo_a/client_a.py and silo_b/client_b.py: full Flower Client subclasses — integrate DataLoader, Bottom Model, cut layer send/receive logic. Leave dp_optimizer hook clearly marked with TODO: Wyatt inserts DP here - Implement fl_server/server.py: VFLStrategy — receives embedding tensors from both silos, concatenates, runs TopModel forward/backward, returns grad tensors to silos - Run first end-to-end VFL training with NO differential privacy: 20 rounds, log loss + AUC to wandb each round - Debug until training converges (validation AUC should improve monotonically for first 10 rounds) - Add learning rate scheduler (ReduceLROnPlateau on val AUC) and early stopping (patience=5 rounds) to both clients - Hyperparameter sweep (wandb sweep): vary lr ∈ [1e-4, 1e-3, 5e-3], dropout ∈ [0.1, 0.2, 0.3], embedding_dim ∈ [16, 32, 64]; run over the no-DP baseline; document best config - Write docs/protocol_spec.md: message types, sizes (bytes), and timing per Flower round | Flower clients A&B + first converging VFL no-DP run logged to wandb + hyperparam sweep results + protocol_spec.md |
| 5 | Wyatt Privacy Lead | - Receive Alex's completed silo_a/client_a.py — locate the TODO comment where the DP hook goes - Implement privacy/privacy_accountant.py: a class PrivacyBudgetTracker that (a) accepts target_epsilon, delta, num_epochs, batch_size, dataset_size in __init__, (b) has step() method that increments round count, (c) has get_epsilon() that calls autodp RDP composition to return current epsilon spent, (d) raises PrivacyBudgetExceededError when get_epsilon() > target_epsilon - Write tests/test_dp.py::test_accountant_budget_exceeded: create tracker with tiny epsilon=0.01, call step() 100 times, assert PrivacyBudgetExceededError is raised - Insert dp_wrapper call into client_a.py at the TODO location Alex marked — replace optimizer line only, do not touch any other code - Run: pytest tests/test_dp.py — all tests should pass - Post Wednesday mid-week report | privacy_accountant.py + PrivacyBudgetExceededError test passing + dp_wrapper inserted into client_a.py |
| 6 | Alex ML Engineer | - Tune Bottom Model B: experiment with skip connection variations; evaluate 1D-CNN variant if time allows - Implement class weighting in BCEWithLogitsLoss: pos_weight = tensor(N_neg/N_pos); verify recall for at-risk class improves - Ablation study: train VFL with (a) Silo A only, (b) Silo B only, (c) both silos; log all to wandb; commit docs/ablation_results.md - Coordinate with Wyatt: integrate his privacy_accountant.py into client_b.py (same pattern as client_a.py) - Run VFL + DP at epsilon=10.0 (loose): confirm model still converges; compare AUC to no-DP run - Run VFL + DP at epsilon=1.0 (strong): observe utility drop; log metrics; note convergence difference - Begin drafting docs/jayquery_paper_draft.md: Introduction and Dataset sections | Ablation study results + DP integrated in both clients + DP runs at epsilon 10.0 and 1.0 logged to wandb + paper intro draft |
| 6 | Wyatt Privacy Lead | - Insert dp_wrapper and privacy_accountant into client_b.py (same pattern as client_a.py, Week 5) — use client_a.py as a reference - Implement privacy/noise_injection.py: a standalone function add_dp_noise_to_embedding(embedding_tensor, sensitivity, epsilon) that adds calibrated Gaussian noise directly to the embedding vector (alternative to DP-SGD — used for comparison experiment). Formula: noise ~ N(0, (sensitivity * sqrt(2*ln(1.25/delta)) / epsilon)^2 ) - Write tests/test_dp.py::test_noise_injection: assert that with epsilon=0.01 the output differs from input, and with epsilon=1000 it is nearly identical - Verify with Alex that epsilon tracker is reporting plausible values after each round (should increase monotonically, never exceed budget) - Read Fredrikson 2015 Sections 1–4 in preparation for Week 7 - Post Wednesday mid-week report | noise_injection.py + test_noise_injection passing + DP running correctly in both clients (confirmed with Alex) |
| 7 | Alex ML Engineer | - Read: Jayaraman & Evans 2019 (full paper) - Run the full epsilon grid: train VFL+DP at epsilon ∈ {0.1, 0.5, 1.0, 2.0, 5.0, 10.0, inf}; save model checkpoints to experiments/checkpoints/eps_{value}/ - Log all runs to wandb with tags: week7, epsilon_{value}; ensure metrics include AUC, F1, Accuracy, Brier - Build experiments/privacy_utility_df.csv from wandb exports: columns [epsilon, AUC, F1, Accuracy, delta_AUC_vs_centralized] - Plot the Privacy-Utility Tradeoff curve (AUC vs. epsilon on log-x scale) with horizontal reference lines for all baselines; save as figures/privacy_utility_curve.png - Identify the Pareto-optimal operating point (knee of the curve) and annotate it on the plot - Write docs/jayquery_paper_draft.md Methods section: dataset, silo construction, model architecture, VFL training loop - Provide Wyatt with attack/inversion_scaffold.py and attack/label_inference_scaffold.py for Week 8 | Full epsilon grid runs + privacy_utility_df.csv + tradeoff curve plot + Methods section of paper drafted + attack scaffolds given to Wyatt |
| 7 | Wyatt Privacy Lead | - Read: Fredrikson 2015 (Sections 1–4), Zhao 2020 iDLG (full paper — focus on Algorithm 1) - Complete wyatt_paper_notes.md for both attack papers before Monday meeting - Write docs/threat_model.md (1–2 pages): (a) Who is the attacker? (honest-but-curious server), (b) What can they observe? (embeddings and gradients), (c) What can they NOT see? (raw data, labels), (d) What are they trying to reconstruct? (imd_band demographic feature). Use Section 1 of Fredrikson 2015 as a template. - Receive attack/inversion_scaffold.py from Alex — read all comments and TODOs carefully - Do NOT start coding the attack yet — spend the last 2 days of Week 7 understanding Algorithm 1 in Zhao 2020 step-by-step. Draw a diagram of the optimization loop. | wyatt_paper_notes.md for attack papers + threat_model.md (1–2 pages) + attack diagram drawn |

🔒  WYATT — Step-by-Step: Implementing the Differential Privacy Wrapper (Weeks 4–6)

Opacus is the primary tool. Follow these steps exactly. Each step is self-contained and testable.

- First, run the Opacus MNIST tutorial at opacus.ai/tutorials — complete it in a notebook before writing any project code. Expected result: training accuracy > 95% with epsilon=10.

- In privacy/dp_wrapper.py, write the make_private() function. The exact Opacus call pattern is:

from opacus import PrivacyEngine

privacy_engine = PrivacyEngine()

dp_model, dp_optimizer, dp_loader = privacy_engine.make_private_with_epsilon(

module=model, optimizer=optimizer, data_loader=data_loader,

target_epsilon=target_epsilon, target_delta=target_delta,

epochs=num_epochs, max_grad_norm=max_grad_norm)

return dp_model, dp_optimizer, dp_loader

- Run pytest tests/test_dp.py::test_dp_wrapper_basic — 1 passed expected.

- For the PrivacyBudgetTracker in privacy_accountant.py, the key autodp call is:

from autodp.autodp_core import Mechanism

# Use dp_optimizer.privacy_engine.get_epsilon(delta) after each epoch

current_eps = dp_optimizer.privacy_engine.get_epsilon(delta=1e-5)

- The noise_injection.py standalone function should use this formula for Gaussian noise std:

sigma = sensitivity * (2 * np.log(1.25 / delta))**0.5 / epsilon

noise = torch.randn_like(embedding) * sigma

return embedding + noise

💡 If stuck: If Opacus raises a 'BatchSampler' error, it means the DataLoader needs to use UniformWithReplacementSampler. Alex will fix the DataLoader — just report the error to him immediately.

## Phase 3: Weeks 8–10 — Red Team Evaluation, Final Analysis & Symposium

| Week | Role | Detailed Activities & Goals | Weekly Deliverable |
| --- | --- | --- | --- |
| 8 | Alex ML Engineer | - Implement experiments/reproduce_all.sh: a shell script that, from a clean clone, runs all experiments in sequence and regenerates all paper figures - Full utility evaluation on held-out test set: all metrics for every epsilon config + all baselines; produce final_results_table.csv - Confusion matrices for: no-DP VFL, epsilon=1.0 VFL, best centralized baseline; save to figures/ - Calibration plot (reliability diagram): predicted probability vs. actual dropout rate — is the model well-calibrated? - Temporal sufficiency analysis: train VFL using only first K weeks of VLE data (K ∈ {1, 3, 5, 8, 10}); plot AUC vs. K; identify earliest actionable week - Feature importance: run SHAP on centralized XGBoost model; plot top-10 predictive VLE activity types - Provide Wyatt with loaded model checkpoints and a data access stub so he can run attacks without touching model training code | Final results table + confusion matrices + calibration plot + temporal analysis + SHAP plot + attack-ready checkpoint loader for Wyatt |
| 8 | Wyatt Privacy Lead | - Read: Jin 2021 CAFE Sections 1–4, Li 2022 full paper - Complete wyatt_paper_notes.md for both papers - Receive attack/inversion_scaffold.py from Alex (provided in Week 7) - Implement the iDLG inversion attack following the scaffold step-by-step (see Wyatt Step-by-Step box below) - Run attack against epsilon=inf (no DP) checkpoint: attempt to reconstruct imd_band for 100 held-out students; record Attack Success Rate (ASR = correct reconstructions / 100) in experiments/attack_results.csv - Run attack against epsilon=1.0 checkpoint: record ASR - Post Wednesday mid-week report describing ASR results vs. expectation | attack/inversion.py functional + ASR results for epsilon=inf and epsilon=1.0 in attack_results.csv |
| 9 | Alex ML Engineer | - Complete the Results section of the paper: all tables (baseline comparison, epsilon grid utility, ablation) and all figures (tradeoff curve, confusion matrices, SHAP, temporal) - Write the Discussion section: limitations (single institution, simulated silos), societal impact (FERPA compliance), model bias analysis (does at-risk prediction differ by demographic group?), future work - Finalize all paper figures to publication quality (consistent axis labels, font sizes, color scheme matching document) - Begin symposium slide deck: lead on slides 1–8 (motivation, architecture, dataset, model, results, tradeoff curve) - Review Wyatt's attack_results.csv and sensitivity analysis; incorporate into the Privacy Analysis section - Coordinate final paper structure with Wyatt; assign Conclusion and References to Week 10 | Results + Discussion sections of paper drafted + symposium slides 1–8 + paper figures finalized |
| 9 | Wyatt Privacy Lead | - Run inversion attack across ALL epsilon values in grid {0.1, 0.5, 1.0, 2.0, 5.0, 10.0, inf}: record ASR for each in attack_results.csv - Run label inference attack (using attack/label_inference_scaffold.py provided by Alex): server attempts to infer at-risk label from gradient shape; record label inference accuracy - Sensitivity analysis: vary max_grad_norm ∈ {0.5, 1.0, 2.0} at epsilon=1.0; run attack for each; record (ASR, AUC) pairs - Implement attack/gradient_monitor.py: a simple function monitor_gradients(gradient_tensor) that computes gradient L2 norm per round and flags anomalously large norms (> 3x running mean) as potential attack indicators - Write docs/privacy_analysis.md: (a) formal (epsilon, delta) guarantees per config table, (b) ASR vs. epsilon table and plot, (c) label inference results, (d) recommended operational epsilon with justification - Prepare symposium slides 9–11 (PSI protocol, DP mechanism, Red Team results) — use the attack_demo.ipynb as visual aid | Full ASR across epsilon grid + label inference results + sensitivity analysis + privacy_analysis.md + symposium slides 9–11 |
| 10 | Alex ML Engineer | - Final code polish: add docstrings to all public functions; ensure pytest --cov reports >70% coverage; fix any remaining TODOs - Write README.md: project description, setup instructions, how to reproduce all experiments (point to reproduce_all.sh) - Write Conclusion + Future Work section of paper; integrate all sections into final docs/jayquery_paper_draft.md - Tag GitHub release v1.0.0: include archived checkpoints, experiment YAML configs, and final figures - Finalize combined symposium slide deck (merge with Wyatt's slides 9–11); 12–15 slides total - Present at Landmark Summer Research Symposium / SCARP Symposium - Write individual SCARP reflection (technical insights, design decisions, what you would do differently) | GitHub v1.0.0 release + complete paper draft + symposium presented + individual reflection submitted |
| 10 | Wyatt Privacy Lead | - Create notebooks/attack_demo.ipynb: step-by-step walkthrough of the inversion attack for a non-technical symposium audience — include visualizations of 'what the attacker sees' vs. 'what they try to reconstruct' - Final code cleanup for privacy/ and attack/ modules: add docstrings to every function you wrote; ensure all tests pass - Finalize poster: lead on the privacy sections (PSI diagram, DP mechanism, Red Team results); print for symposium - Proofread the full paper draft; add References section (BibTeX entries for all papers you read) - Present at Landmark Summer Research Symposium / SCARP Symposium - Write individual SCARP reflection: what you learned about cryptography and privacy engineering, what was hardest, what you are proud of | attack_demo.ipynb + poster printed + references section + symposium presented + individual reflection submitted |

🔒  WYATT — Step-by-Step: Implementing the Model Inversion Attack (Week 8)

This is your Red Team work. You are playing the role of an attacker who has access to the embedding vectors but NOT the raw student data. Your goal is to see if you can guess a student's imd_band (deprivation index) from their embedding alone.

- Open attack/inversion_scaffold.py (provided by Alex in Week 7). Read every comment. The scaffold has four clearly marked TODO sections.

- TODO 1 — Load a checkpoint: use the loader stub Alex provided. This gives you access to the model and a set of real embeddings + labels.

checkpoint = torch.load('experiments/checkpoints/eps_inf/model.pt')

bottom_model_a = checkpoint['bottom_model_a']

- TODO 2 — Initialize dummy input: create a random tensor the same shape as Silo A input (batch_size x 12) with requires_grad=True.

dummy_input = torch.randn(1, 12, requires_grad=True)  # one student at a time

- TODO 3 — The optimization loop (Algorithm 1 from Zhao 2020). Run for 200 iterations:

optimizer_attack = torch.optim.LBFGS([dummy_input], lr=0.1)

for i in range(200):

def closure():

optimizer_attack.zero_grad()

dummy_emb = bottom_model_a(dummy_input)

loss = ((dummy_emb - real_embedding) ** 2).sum()  # gradient matching

loss.backward()

return loss

optimizer_attack.step(closure)

- TODO 4 — Measure success: after the loop, check if dummy_input[imd_band_column].argmax() == true_imd_band. Record as success (1) or failure (0) in attack_results.csv.

- Run against 100 held-out students for epsilon=inf and epsilon=1.0. Expected: ASR at epsilon=inf is meaningfully above 1/5 (random = 20% for 5 imd_band categories). ASR at epsilon=1.0 should be much lower.

💡 If stuck: If the attack loss doesn't decrease below 1.0 after 200 iterations, check that bottom_model_a is in eval mode (model.eval()) and that gradients are not being clipped. Post the loss curve in Slack.

6. Experiments & Studies

All experiments logged to wandb. Every run uses seed=42. Alex orchestrates all experiments via YAML configs in experiments/. Wyatt runs only the attack experiments (9–11) using checkpoints Alex provides — Wyatt does not modify training configs.

| # | Experiment | Description | Metrics | Owner |
| --- | --- | --- | --- | --- |
| 1 | Centralized Baselines | Train LogReg, Full MLP, XGBoost, and isolated-silo MLPs on merged dataset. Sets performance ceiling. | AUC-ROC, Accuracy, F1, Precision, Recall, Brier | Alex |
| 2 | VFL No-DP Baseline | Full VFL (SplitNN) without DP. Best achievable VFL performance. Quantifies VFL overhead vs. centralized. | AUC-ROC, Accuracy, communication overhead (MB/round), convergence rounds | Alex |
| 3 | DP-SGD Epsilon Grid | VFL+DP at epsilon ∈ {0.1, 0.5, 1.0, 2.0, 5.0, 10.0}, delta=1e-5. Core privacy-utility experiment. | AUC-ROC, F1, actual epsilon spent, convergence rounds to AUC=0.70 | Both |
| 4 | DP Noise Type Comparison | Gaussian (DP-SGD) vs. Laplace (noise_injection.py) at equivalent epsilon=1.0. Which preserves more utility? | AUC-ROC at convergence, training loss variance per round | Alex + Wyatt |
| 5 | Clipping Norm Sensitivity | Vary max_grad_norm ∈ {0.5, 1.0, 2.0} at epsilon=1.0. How does clipping affect utility and attack resistance? | AUC-ROC, ASR (Attack Success Rate) | Wyatt |
| 6 | PSI Overhead Benchmark | Run PSI for ID set sizes ∈ {500, 1k, 2k, 5k, 10k}. Scalability analysis. | Wall-clock time (ms), message bytes exchanged | Wyatt |
| 7 | Silo Contribution Ablation | Train on only Silo A, only Silo B, both (VFL), full merged. Value of collaboration. | AUC-ROC for each configuration | Alex |
| 8 | Embedding Dimension Sweep | Bottom model output dim ∈ {8, 16, 32, 64}. Minimum dimension that preserves utility. | AUC-ROC, reconstruction MSE (attack proxy) | Alex |
| 9 | Model Inversion Attack (iDLG) | For each epsilon: run 200-iter gradient-matching attack on 100 held-out students. Reconstruct imd_band. | ASR (Attack Success Rate), per-category reconstruction error | Wyatt |
| 10 | Label Inference Attack | Server infers Silo B at-risk labels from returned gradient tensors without seeing labels directly. | Label inference accuracy (random baseline = 50%) | Wyatt |
| 11 | Temporal Sufficiency Analysis | Train VFL using first K weeks of VLE data (K ∈ {1,3,5,8,10}). Earliest actionable prediction point. | AUC-ROC vs. week K | Alex |
| 12 | Privacy-Utility Tradeoff Curve | Aggregate Exp. 3 to produce canonical epsilon vs. AUC curve. Identify Pareto-optimal operating epsilon. | AUC-ROC vs. epsilon (plot + delta_AUC table), recommended epsilon | Both |

7. Complete Deliverables Summary

## 7.1 Alex Pellet (Student A) — Weekly Deliverables

- Week 1: GitHub repo + directory structure + SETUP.md + EDA notebook + wandb project + architecture diagram

- Week 2: Silo A features file + Silo B features file + DATA_DICTIONARY.md + PSI scaffold for Wyatt

- Week 3: DataLoaders (A+B) + all 4 centralized baselines + baseline_results.md + Flower server/client scaffolds

- Week 4: Bottom Models A & B + Top Model + unit tests + eval_utils.py + smoke test

- Week 5: Flower clients A & B + first converging VFL no-DP run + hyperparameter sweep + protocol_spec.md

- Week 6: Ablation study + DP integrated in both clients + DP runs at epsilon=10.0 and 1.0 + paper intro/dataset draft

- Week 7: Full epsilon grid runs + privacy_utility_df.csv + tradeoff curve plot + Methods section + attack scaffolds for Wyatt

- Week 8: Final results table + confusion matrices + calibration plot + temporal analysis + SHAP plot + checkpoint loaders

- Week 9: Results + Discussion sections of paper + symposium slides 1–8 + publication-quality figures

- Week 10: README.md + GitHub v1.0.0 + Conclusion section + final paper integrated + symposium presented + reflection

## 7.2 Wyatt Wilfong (Student B) — Weekly Deliverables

- Week 1: Environment verified (all imports passing screenshot) + wyatt_paper_notes.md first entry + repo cloned

- Week 2: ecdh_utils.py (generate_keypair + blind_id) + test_ecdh_basic passing + paper notes for 2 privacy papers

- Week 3: Full PSI protocol (psi_client.py + psi_server.py) + correctness test passing + ordered_id_list.json + psi_protocol.md

- Week 4: dp_wrapper.py with make_private() + test_dp_wrapper_basic passing + Opacus MNIST demo run + paper notes

- Week 5: privacy_accountant.py + PrivacyBudgetExceededError test passing + dp_wrapper inserted into client_a.py

- Week 6: noise_injection.py + test_noise_injection passing + DP confirmed working in both clients + paper notes for DP papers

- Week 7: wyatt_paper_notes.md for attack papers + threat_model.md (1–2 pages) + attack optimization loop diagram

- Week 8: attack/inversion.py functional + ASR for epsilon=inf and epsilon=1.0 in attack_results.csv + paper notes for CAFE and Li 2022

- Week 9: Full ASR across epsilon grid + label inference results + sensitivity analysis + privacy_analysis.md + symposium slides 9–11

- Week 10: attack_demo.ipynb + poster printed + References section of paper + symposium presented + reflection

## 7.3 Joint Deliverables

- Week 3: PSI-aligned silo data files — Alex confirms DataLoaders use Wyatt's ordered_id_list.json correctly

- Week 5: First converging VFL+DP run — Wyatt's dp_wrapper hooked into Alex's client, training logged to shared wandb

- Week 7: Full epsilon grid — Alex runs training, Wyatt confirms epsilon tracker values are correct

- Week 9: Symposium slides merged (12–15 total) + poster draft reviewed by Dr. Li

- Week 10: JayQuery final paper (docs/jayquery_paper_draft.md) + GitHub v1.0.0 release + symposium presented + SCARP reflections

8. Mentoring, Reporting & Escalation Cadence

| Cadence | Format & Content |
| --- | --- |
| Weekly Meeting (Monday, 1 hr) | 20-min stand-up: each student reports progress vs. this week's deliverables. 40-min deep-dive: one technical blocker or design question. Wyatt always brings his paper notes. Alex brings his design notes. |
| Daily GitHub Commit | Required every working day. Format: [wkN][Alex/Wyatt] description. Wyatt: even 5 lines of scaffold progress counts — commit often. |
| Wednesday Mid-Week Report | Slack to Dr. Li. Exactly 3 bullets: (1) What I did Mon–Wed, (2) Plan for Wed–Fri, (3) Blockers. Wyatt: Dr. Li will respond to blockers within 24 hours. |
| Weekly Pull Request | Each student opens one PR on Friday. Must have passing pytest before requesting review. Mentor reviews for code quality, documentation, and correctness. |
| Wyatt Escalation Rule | If Wyatt is stuck for more than 60 minutes on a single step, post in Slack immediately with: (a) the exact error message, (b) what you tried, (c) which step number you are on from this document. Do not wait for Wednesday. |
| Shared wandb Dashboard | Both students tag runs with their name and week. Dr. Li reviews wandb logs before each Monday meeting. |

9. Risk Register & Contingency Plans

| Risk | Likelihood | Mitigation & Contingency | Owner |
| --- | --- | --- | --- |
| Wyatt gets blocked on PSI cryptography for multiple days | High (freshman, new topic) | Alex provides ecdh_utils_scaffold.py with every function stub and exact code patterns. Dr. Li runs a 30-min pair-programming session in Week 2 if PSI not passing tests by Wednesday. | Dr. Li + Alex |
| Opacus DP-SGD incompatible with custom SplitNN backward pass | High | Opacus requires standard nn.Module. Alex ensures bottom models use only standard PyTorch ops. Fallback: Wyatt uses noise_injection.py standalone approach instead of DP-SGD — same epsilon guarantee, simpler integration. | Alex + Wyatt |
| PSI output misalignment corrupts training data pairing | Medium | Alex writes validate_alignment() utility (Week 3) that checks the first 10 IDs in both silos match the PSI output. Run this before every training run. | Alex |
| OULAD class imbalance causes model to predict majority always | High | Alex applies SMOTE + BCEWithLogitsLoss class weighting. Monitor recall separately. If recall < 0.4 for at-risk class, downsample majority to 2:1 ratio. | Alex |
| Wyatt's attack produces near-random ASR even at epsilon=inf | Medium | Fallback to CAFE attack (Jin 2021) which is stronger for VFL — Alex provides CAFE scaffold in Week 8. Supplement with embedding cosine similarity as a passive privacy metric. | Wyatt + Alex |
| VFL training diverges or oscillates (loss not decreasing) | Medium | Reduce lr to 1e-4. Add gradient clipping (nn.utils.clip_grad_norm_, max=1.0) before DP noise. Check that both silos step optimizers in the same round. | Alex |
| Scope overrun: 12 experiments take too long | Medium | Priority tier: MUST run (1,2,3,7,9,12). SHOULD run (4,5,10,11). NICE TO HAVE (6,8). Decide by end of Week 7 with Dr. Li approval. | Both |

10. Symposium Presentation Outline

Target: 12–15 slides, 15-minute presentation + 5-minute Q&A. Alex leads slides 1–8 (system + ML results). Wyatt leads slides 9–11 (privacy + red team). Joint closing slides 12–14.

- Title Slide — Alex presents: JayQuery, student names, Dr. Li, SCARP 2026

- The Problem — Alex: FERPA siloed data paralysis; why merging records is illegal; cost in student retention outcomes

- Our Solution — Alex: VFL system architecture diagram; three-layer overview (PSI → SplitNN → Top Model)

- Dataset — Alex: OULAD description; two simulated silos; class distribution of dropout labels

- System Architecture Deep Dive — Alex: Flower server/client diagram; cut layer communication; gradient flow animation

- ML Models — Alex: Bottom Model A (demographics), Bottom Model B (VLE), Top Model; data flow diagram

- Results: Centralized vs. VFL — Alex: baseline comparison table; VFL no-DP vs. baselines; ablation results

- Privacy-Utility Tradeoff Curve — Alex: the key result figure; recommended operating epsilon; what we give up for privacy

- PSI Protocol — Wyatt presents: what PSI solves (the matching problem); step-by-step animation; timing results

- Differential Privacy — Wyatt: what epsilon means in plain English ('a needle in a haystack of noise'); how Opacus adds the noise; budget tracking

- Red Team Results — Wyatt: what a Model Inversion Attack is; ASR at epsilon=inf vs. epsilon=1.0; show attack_demo.ipynb plot

- Key Finding (Joint) — Both: at epsilon=1.0, VFL achieves AUC [X] vs. centralized [Y] while reducing inversion ASR from [Z%] to near-random

- Broader Impact (Joint) — Both: Smart Campus vision; FERPA-compliant early-alert; respecting digital rights

- Thank You + Questions — Both present; Alex handles ML questions; Wyatt handles privacy/attack questions

JayQuery SCARP 2026 — Elizabethtown College Computer Science

Dr. Peilong Li (Mentor)  |  Alex Pellet — System Architect & ML Engineer  |  Wyatt Wilfong — Privacy & Security Lead